## ReadMe
MIL-STD-882E w/Change 1 — System Safety Basis of Estimate (BOE) Model
How it works
1. Inputs: enter program start/end, the two SAR anchor estimates (P50 and P90 hours), the complexity level, the SwCI level, and the quantity drivers (subsystems, test events, ECPs, reviews).
2. Milestones: define your program milestones as months-after-start (or type a hard date in the override column). Every task's dates hang off these milestones.
3. BOE: one row per 882E task (and per LOE item). Each row is anchored one of three ways:
SAR = ratio × SAR P50 hours × quantity (documents and analyses — the default)
LOE = hours per month × months between its start and end milestones × quantity (meetings, HTS upkeep, reporting)
FIXED = hours entered directly × quantity (anything you want to hard-size)
The result is multiplied by the complexity factor (if 'Apply Cx' = Y) and the SwCI multiplier (if 'Apply SwCI' = Y).
P90 = P50 × (SAR P90 ÷ SAR P50) unless a per-row P90 ratio override is entered.
Set 'Tasked' to N to remove a task from the estimate without deleting the row (only Sections 3 and 4 of the standard are mandatory; tasks are cited by contract).
4. Phasing: spreads each row's hours evenly across its start–end window by month, and shows the monthly FTE load. Switch P50/P90 on the Inputs sheet.
5. Timeline: Gantt view — milestone diamonds and task bars — generated from Milestones and BOE. Nothing is typed on this sheet.
6. Summary: totals by task section, P50 vs P90, average and peak FTE.
Cell colors
Blue text on light-yellow fill = input you can change. Black = formula. Green = link to another sheet. Yellow fill = key assumption.
Assumption notes
Default anchor ratios are planning assumptions typical of DoD system safety programs; they are not from the standard. Calibrate them against your own actuals.
Task 103 and Task 302 are the equivalents of 102/301 for other functional disciplines and default to Not Tasked. Tasks 402/403 (explosives/EOD) default to Not Tasked.
Section 4.4 software Level-of-Rigor (LOR) work is not a numbered task but is real effort; it is included as row 'SW-LOR' and scaled by the SwCI multiplier.
Hours per FTE-month default (156) ≈ 1,872 productive hours per year ÷ 12.
Source document: MIL-STD-882E w/CHANGE 1, 27 September 2023 (ASSIST). Task numbers and titles are taken from it.
Adding rows
Milestones: up to 30 rows are pre-wired. BOE: insert a row inside the table and copy the formulas down from the row above; Phasing and Timeline reference BOE rows 6–60.

## Summary
Estimate Summary
Complexity: Moderate (1.00) ¦ SwCI 2 (×1.30) ¦ SAR P50 800 h, P90 1,200 h
Section | Rows tasked | P50 hours | P90 hours | P50 share | P90 ÷ P50
100 Management | 8 | 2434.924 | 3652.386 | 20.37% | 1.5
200 Analysis | 9 | 5424 | 8136 | 45.38% | 1.5
300 Evaluation | 3 | 1920 | 2880 | 16.06% | 1.5
400 Verification | 2 | 1352 | 2028 | 11.31% | 1.5
LOE / Other | 3 | 822.2752 | 1233.4127 | 6.879% | 1.5
TOTAL | 25 | 11953.1992 | 17929.7988 | 100% | 1.5
Program metrics
Program duration (months) | 35.8768
Average FTE — P50 | 2.1357
Average FTE — P90 | 3.2036
Peak monthly FTE (phasing basis) | 4.1304
Peak month hours (phasing basis) | 644.35
Phasing basis in use | P50
Hours per FTE-month | 156
Anchor-ratio check: SAR-anchored rows as a multiple of one SAR (P50, before factors)
Sum of SAR ratios × qty (tasked rows) | 10.9 | e.g. 9.5 means the SAR-anchored documents total ~9.5 SARs of effort. Useful sanity check against your historical program totals.

## Inputs
Program Inputs & Assumptions
Blue cells on yellow are inputs. Everything else in the workbook derives from this sheet and Milestones.
Program start date | 2027-01-04 |  |  | Month 1 of the timeline. Milestones are offsets from this date.
Program end date | 2029-12-31 |  |  | Timeline and phasing stop here (max 72 months).
Hours per FTE-month | 156 |  |  | Used to convert monthly hours to FTE loading. 1,872 hrs/yr ÷ 12.
Phasing basis (P50 / P90) | P50 |  |  | Which estimate the Phasing and Timeline sheets spread by month.
SAR anchor (Task 301 Safety Assessment Report)
SAR P50 hours | 800 |  |  | User estimate: hours to produce the SAR at a 50% confidence level. All SAR-anchored rows scale from this.
SAR P90 hours | 1200 |  |  | User estimate: hours at 90% confidence. The P90/P50 ratio drives every other row's P90 unless overridden.
P90 / P50 ratio | 1.5 |  |  | Derived. Applied to all rows without a per-row override.
Complexity
Program complexity level | Moderate | Level | Factor | Pick from the table at right.
Complexity factor (lookup) | 1 | Low | 0.8
Complexity factor override (optional) |  | Moderate | 1 | Leave blank to use the lookup. Enter e.g. 1.25 to override.
Effective complexity factor | 1 | High | 1.3 | Multiplies every BOE row flagged 'Apply Cx = Y'.
|  | Very High | 1.6
Complexity guide: Low = mature design, few interfaces, no safety-significant software. Moderate = typical. High = new design, many subsystems/interfaces, safety-significant software. Very High = autonomous/novel energy storage, SoS interfaces, multiple risk-acceptance authorities.
Software criticality (Section 4.4)
Software Criticality Index (SwCI 1–5) | 2 | SwCI | Multiplier | From Table V: severity × software control category. BMS firmware that alone opens contactors on a Catastrophic hazard = SwCI 1; with an independent HW protection layer = SwCI 2–3.
SwCI multiplier (lookup) | 1.3 | 1 | 1.5 | Multiplies rows flagged 'Apply SwCI = Y' (software-touching analyses, verification, LOR).
|  | 2 | 1.3
|  | 3 | 1.15
|  | 4 | 1
|  | 5 | 0.8
Multiplier rationale: SwCI 1 adds code-level analysis and in-depth safety testing (Table V); SwCI 5 means no safety-specific software analysis.
Quantity drivers
Number of subsystems analyzed (Task 204) | 6 |  |  | e.g., pack/modules, BMS, contactor/precharge, HV distribution, thermal mgmt, charger interface.
Number of test events (Task 303) | 8 |  |  | Each needs hazard review, Safety Release support, post-test analysis.
Expected ECPs / change notices reviewed (Task 304) | 20 |  |  | Over the program life.
Government reviews / audits / boards supported (Task 104) | 6 |  |  | SRR, PDR, CDR, TRR, safety boards, audits.
Design reviews with safety packages (SRR/PDR/CDR/TRR) | 4 |  |  | Safety data package preparation per review.

## Milestones
Program Milestones
Enter each milestone as months after program start (column C), or type a hard date in column D to override. Column E is what the BOE uses. Keep names unique — the BOE picks them from a dropdown.
# | Milestone | Months after start | Date override (optional) | Milestone date (used) | Description
1 | Program Start | 0 |  | 2027-01-04 | Contract award / program kickoff.
2 | SRR | 3 |  | 2027-04-04 | System Requirements Review.
3 | SFR | 6 |  | 2027-07-04 | System Functional Review.
4 | PDR | 10 |  | 2027-11-04 | Preliminary Design Review.
5 | CDR | 16 |  | 2028-05-04 | Critical Design Review.
6 | TRR | 24 |  | 2029-01-04 | Test Readiness Review.
7 | Test Start | 25 |  | 2029-02-04 | First safety-relevant test event (bench / HIL / pack abuse).
8 | Test Complete | 31 |  | 2029-08-04 | Last test event complete.
9 | SAR Submittal | 33 |  | 2029-10-04 | Safety Assessment Report delivered for risk acceptance.
10 | Program End |  | 2029-12-31 | 2029-12-31 | Contract end — taken from Inputs.
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Formulas:
Milestone date (used) = IF([Milestone]="","",IF([Date override (optional)]<>"",[Date override (optional)],IF([Months after start]<>"",EDATE(Inputs!$B4,[Months after start]),"")))

## BOE
Basis of Estimate — MIL-STD-882E w/Change 1 Tasks
Anchor: SAR = ratio × SAR P50 × Qty ¦ LOE = hrs/month × months in window × Qty ¦ FIXED = hours × Qty. Then × complexity (if Apply Cx=Y) × SwCI multiplier (if Apply SwCI=Y). P90 = P50 × P90/P50 ratio (or row override).
SAR P50 anchor: | 800 | Cx factor: | 1 | SwCI mult: | 1.3 | P90/P50: | 1.5
Task | Section | Title / Work Element | Deliverable | Tasked (Y/N) | Anchor type | Driver value (ratio of SAR ¦ hrs/month ¦ hours) | Qty | Apply Cx (Y/N) | Apply SwCI (Y/N) | Start milestone | Start offset (wks) | End milestone | End offset (wks) | Start date | End date | Months | P50 hours | P90 ratio override | P90 hours | Basis / assumption
101 | 100 Management | Hazard identification & mitigation effort using the system safety methodology (program execution) | Program execution | Y | LOE | 20 | 1 | Y | N | Program Start | 0 | Program End | 0 | 2027-01-04 | 2029-12-31 | 35.8768 | 717.5359 |  | 1076.3039 | Ongoing management of the safety effort: planning, roles, subcontractor flow-down, status reporting, IMS inputs (101.2.1–101.2.9). Sized as a monthly run-rate.
102 | 100 Management | System Safety Program Plan (SSPP) | SSPP | Y | SAR | 0.4 | 1 | Y | N | Program Start | 0 | SRR | 0 | 2027-01-04 | 2027-04-04 | 2.9569 | 320 |  | 480 | Plan covering scope, interfaces, organization, milestones, requirements, analyses, V&V, audits, training, incident reporting (102.2.1–102.2.11). ~40% of a SAR.
103 | 100 Management | Hazard Management Plan (HMP) — other functional disciplines | HMP | N | SAR | 0.3 | 1 | Y | N | Program Start | 0 | SRR | 0 | 2027-01-04 | 2027-04-04 | 2.9569 | 0 |  | 0 | Equivalent of the SSPP for a non-system-safety discipline (103). Default Not Tasked; turn on if a separate discipline plan is contracted.
104 | 100 Management | Support of Government reviews / audits / boards | Review support | Y | SAR | 0.05 | 6 | Y | N | SRR | -4 | Program End | 0 | 2027-03-07 | 2029-12-31 | 33.8398 | 240 |  | 360 | Per review/audit/board (104.2.1): prep, attendance, action closure. ~5% of a SAR each × number of reviews (Inputs).
105 | 100 Management | Integrated Product Team / Working Group support | IPT / SSWG participation | Y | LOE | 12 | 1 | Y | N | Program Start | 0 | Program End | 0 | 2027-01-04 | 2029-12-31 | 35.8768 | 430.5216 |  | 645.7823 | Standing membership in designated IPTs and the System Safety Working Group (105.2). Monthly run-rate; raise if several IPTs are supported.
106a | 100 Management | Hazard Tracking System — establish | HTS (initial) | Y | SAR | 0.15 | 1 | Y | N | Program Start | 0 | SRR | 0 | 2027-01-04 | 2027-04-04 | 2.9569 | 120 |  | 180 | Stand up the closed-loop HTS with the required data elements (106.2) and Government access controls (106.2.1).
106b | 100 Management | Hazard Tracking System — maintain | HTS (upkeep) | Y | LOE | 8 | 1 | Y | N | SRR | 0 | Program End | 0 | 2027-04-04 | 2029-12-31 | 32.9199 | 263.3593 |  | 395.039 | Keep hazard records, risk assessments, mitigation status and acceptance current through the life-cycle (106.2, 4.3.8).
107 | 100 Management | Hazard Management Progress Report | Periodic progress reports | Y | LOE | 4 | 1 | Y | N | Program Start | 0 | Program End | 0 | 2027-01-04 | 2029-12-31 | 35.8768 | 143.5072 |  | 215.2608 | Periodic report summarizing hazard status, risk assessments, mitigations and open actions (107.2). Assumes monthly.
108 | 100 Management | Hazardous Materials Management Plan (HMMP) | HMMP + HAZMAT list | Y | SAR | 0.25 | 1 | Y | N | Program Start | 0 | PDR | 0 | 2027-01-04 | 2027-11-04 | 9.9877 | 200 |  | 300 | HAZMAT identification, categorization, tracking (108.2.1–108.2.4). Relevant to Li-ion cells, electrolyte, coolant.
201 | 200 Analysis | Preliminary Hazard List (PHL) | PHL | Y | SAR | 0.2 | 1 | Y | N | Program Start | 0 | SRR | 0 | 2027-01-04 | 2027-04-04 | 2.9569 | 160 |  | 240 | Early hazard list from legacy/similar-system data and lessons learned (201.2.1–201.2.3).
202 | 200 Analysis | Preliminary Hazard Analysis (PHA) | PHA report | Y | SAR | 0.6 | 1 | Y | N | SRR | 0 | SFR | 4 | 2027-04-04 | 2027-08-01 | 3.9097 | 480 |  | 720 | Initial risk assessment per hazard across the 202.2.2 hazard sources (energy, software, HAZMAT, environment, human factors, etc.).
203 | 200 Analysis | System Requirements Hazard Analysis (SRHA) | SRHA + requirements traceability | Y | SAR | 0.5 | 1 | Y | Y | SRR | 0 | CDR | 0 | 2027-04-04 | 2028-05-04 | 13.0103 | 520 |  | 780 | Derive safety design requirements, incorporate into specs, assess compliance through design (203.2.1–203.2.3). Continues through CDR.
204 | 200 Analysis | Subsystem Hazard Analysis (SSHA) | SSHA report(s) | Y | SAR | 0.3 | 6 | Y | Y | PDR | 0 | CDR | 4 | 2027-11-04 | 2028-06-01 | 6.8994 | 1872 |  | 2808 | Per subsystem (Inputs qty): component failure modes, software causal factors, human error (204.2.1). ~30% of a SAR per subsystem.
205 | 200 Analysis | System Hazard Analysis (SHA) | SHA report | Y | SAR | 0.8 | 1 | Y | Y | PDR | 0 | CDR | 8 | 2027-11-04 | 2028-06-29 | 7.8193 | 832 |  | 1248 | Subsystem interface and interrelationship hazards, software and human interfaces (205.2.1); design-change evaluation (205.2.4).
206 | 200 Analysis | Operating & Support Hazard Analysis (O&SHA) | O&SHA report | Y | SAR | 0.6 | 1 | Y | N | CDR | 0 | TRR | 0 | 2028-05-04 | 2029-01-04 | 8.0493 | 480 |  | 720 | Operations, maintenance, test, storage, transport, disposal hazards; procedures, warnings, PPE (206.2.1–206.2.5).
207 | 200 Analysis | Health Hazard Analysis (HHA) | HHA report | Y | SAR | 0.35 | 1 | Y | N | PDR | 0 | CDR | 0 | 2027-11-04 | 2028-05-04 | 5.9795 | 280 |  | 420 | Chemical, electrical, thermal, noise and other health hazards per 207.2.2–207.2.3 categories (electrolyte, HF, HV).
208 | 200 Analysis | Functional Hazard Analysis (FHA) | FHA + SCF/SCI list | Y | SAR | 0.5 | 1 | Y | Y | SRR | 0 | PDR | 0 | 2027-04-04 | 2027-11-04 | 7.0308 | 520 |  | 780 | Loss/degraded/out-of-sequence function hazards, identify SCFs/SCIs, map to HW/SW/human (208.2.1). Feeds the fault-injection list.
209 | 200 Analysis | System-of-Systems Hazard Analysis | SoS HA report | N | SAR | 0.4 | 1 | Y | N | PDR | 0 | CDR | 0 | 2027-11-04 | 2028-05-04 | 5.9795 | 0 |  | 0 | Unique SoS hazards and traceability (209.2.1–209.2.4). Default Not Tasked; enable if the vehicle integrates into a larger SoS.
210 | 200 Analysis | Environmental Hazard Analysis (EHA) | EHA report | Y | SAR | 0.35 | 1 | Y | N | PDR | 0 | CDR | 0 | 2027-11-04 | 2028-05-04 | 5.9795 | 280 |  | 420 | Environmental impacts, HAZMAT and pollutant hazards across the life-cycle (210.2.2–210.2.5).
301 | 300 Evaluation | Safety Assessment Report (SAR) — ANCHOR | SAR | Y | SAR | 1 | 1 | Y | N | TRR | 0 | SAR Submittal | 0 | 2029-01-04 | 2029-10-04 | 8.9692 | 800 |  | 1200 | The anchor estimate. Ratio 1.00 by definition; hours come straight from Inputs SAR P50/P90. Summarizes hazards, residual risk, and recommendations for risk acceptance (301.2).
302 | 300 Evaluation | Hazard Management Assessment Report (HMAR) | HMAR | N | SAR | 0.8 | 1 | Y | N | TRR | 0 | SAR Submittal | 0 | 2029-01-04 | 2029-10-04 | 8.9692 | 0 |  | 0 | Equivalent of the SAR for another functional discipline (302). Default Not Tasked.
303 | 300 Evaluation | Test & Evaluation participation | Safety Releases, post-test analyses, T&E repository | Y | SAR | 0.1 | 8 | Y | N | Test Start | -8 | Test Complete | 4 | 2028-12-10 | 2029-09-01 | 8.7064 | 640 |  | 960 | Per test event (Inputs qty): hazard review of test setup/procedures, Safety Release, post-test analysis and HTS update (303.2.1–303.2.3). Your fault-injection campaign lives here.
304 | 300 Evaluation | Review of ECPs, change notices, deficiency reports, waivers | Change reviews | Y | SAR | 0.03 | 20 | Y | N | CDR | 0 | Program End | 0 | 2028-05-04 | 2029-12-31 | 19.9097 | 480 |  | 720 | Per change (Inputs qty): hazard impact assessment and HTS update (304.2). ~3% of a SAR each.
401 | 400 Verification | Safety Verification (tests, demonstrations, induced/simulated failures) | Safety verification report | Y | SAR | 0.7 | 1 | Y | Y | CDR | 0 | Test Complete | 0 | 2028-05-04 | 2029-08-04 | 15.0144 | 728 |  | 1092 | Define and perform tests/demos/analyses on safety-significant HW, SW and procedures; induced or simulated failures (401.2). Fault-injection test planning, execution support and reporting.
402 | 400 Verification | Explosives Hazard Classification Data | Hazard classification package | N | SAR | 0.5 | 1 | Y | N | CDR | 0 | TRR | 0 | 2028-05-04 | 2029-01-04 | 8.0493 | 0 |  | 0 | Not applicable to a battery program unless energetics are present. Default Not Tasked.
403 | 400 Verification | Explosive Ordnance Disposal Data | EOD source data | N | SAR | 0.3 | 1 | Y | N | CDR | 0 | TRR | 0 | 2028-05-04 | 2029-01-04 | 8.0493 | 0 |  | 0 | Not applicable unless explosives are present. Default Not Tasked.
SW-LOR | 400 Verification | Software Level-of-Rigor tasks (Section 4.4, Table V) | LOR analysis & test evidence | Y | SAR | 0.6 | 1 | Y | Y | PDR | 0 | TRR | 0 | 2027-11-04 | 2029-01-04 | 14.0287 | 624 |  | 936 | Not a numbered task but required by 4.4.1–4.4.3: requirements/architecture/design/code analysis and safety-specific testing per SwCI. Strongly scaled by the SwCI multiplier.
LOE-1 | LOE / Other | System Safety Working Group meetings | Meeting prep, attendance, minutes, actions | Y | LOE | 8 | 1 | Y | N | Program Start | 0 | Program End | 0 | 2027-01-04 | 2029-12-31 | 35.8768 | 287.0144 |  | 430.5216 | Assumes a monthly SSWG: 2 hrs meeting + prep/minutes/actions for the safety lead. Increase Qty for additional attendees.
LOE-2 | LOE / Other | Design review safety data packages (SRR/PDR/CDR/TRR) | Safety briefing packages | Y | SAR | 0.1 | 4 | Y | N | SRR | -6 | TRR | 0 | 2027-02-21 | 2029-01-04 | 22.4394 | 320 |  | 480 | Per design review (Inputs qty): hazard status briefing, risk matrix, open items. Distinct from Task 104 attendance.
LOE-3 | LOE / Other | Safety program management, BOE/EVM upkeep, travel | Internal management | Y | LOE | 6 | 1 | N | N | Program Start | 0 | Program End | 0 | 2027-01-04 | 2029-12-31 | 35.8768 | 215.2608 |  | 322.8912 | Internal overhead not tied to a task: EVM/BOE maintenance, scheduling, travel. Complexity not applied.
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
[17 empty] | 0 |  | 0
|  | TOTAL (tasked rows) | [14 empty] | 11953.1992 |  | 17929.7988
Formulas:
Start date = IFERROR(INDEX(Milestones!$E5:E34,MATCH([Start milestone],Milestones!$B5:B34,0))+N([Start offset (wks)])*7,"")
End date = IFERROR(INDEX(Milestones!$E5:E34,MATCH([End milestone],Milestones!$B5:B34,0))+N([End offset (wks)])*7,"")
Note on G5: SAR rows: fraction of the SAR P50 hours (0.60 = 60% of a SAR). LOE rows: hours per month. FIXED rows: hours. Defaults are planning assumptions — calibrate to your actuals.
Note on H5: Multiplier. For per-unit tasks this links to the Inputs quantity drivers (green). Override by typing a number.
Note on S5: Optional per-row P90/P50 ratio. Blank = use the SAR-derived ratio from Inputs.

## Phasing
Monthly Phasing — hours spread evenly across each row's start–end window
Basis: P50 ¦ Hours per FTE-month: 156
|  |  |  | Month # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Task | Title | Start | End | Hours | 2027-01-04 | 2027-02-04 | 2027-03-04 | 2027-04-04 | 2027-05-04 | 2027-06-04 | 2027-07-04 | 2027-08-04 | 2027-09-04 | 2027-10-04 | 2027-11-04 | 2027-12-04 | 2028-01-04 | 2028-02-04 | 2028-03-04 | 2028-04-04 | 2028-05-04 | 2028-06-04 | 2028-07-04 | 2028-08-04 | 2028-09-04 | 2028-10-04 | 2028-11-04 | 2028-12-04 | 2029-01-04 | 2029-02-04 | 2029-03-04 | 2029-04-04 | 2029-05-04 | 2029-06-04 | 2029-07-04 | 2029-08-04 | 2029-09-04 | 2029-10-04 | 2029-11-04 | 2029-12-04
101 | Hazard identification & mitigation effort using the system safety methodology (program execution) | 2027-01-04 | 2029-12-31 | 717.5359 | 20.351 | 18.3815 | 20.351 | 19.6945 | 20.351 | 19.6945 | 20.351 | 20.351 | 19.6945 | 20.351 | 19.6945 | 20.351 | 20.351 | 19.038 | 20.351 | 19.6945 | 20.351 | 19.6945 | 20.351 | 20.351 | 19.6945 | 20.351 | 19.6945 | 20.351 | 20.351 | 18.3815 | 20.351 | 19.6945 | 20.351 | 19.6945 | 20.351 | 20.351 | 19.6945 | 20.351 | 19.6945 | 18.3815
102 | System Safety Program Plan (SSPP) | 2027-01-04 | 2027-04-04 | 320 | 109.011 | 98.4615 | 109.011 | 3.5165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | Hazard Management Plan (HMP) — other functional disciplines | 2027-01-04 | 2027-04-04 | 0
104 | Support of Government reviews / audits / boards | 2027-03-07 | 2029-12-31 | 240 | 0 | 0 | 6.5179 | 6.9835 | 7.2163 | 6.9835 | 7.2163 | 7.2163 | 6.9835 | 7.2163 | 6.9835 | 7.2163 | 7.2163 | 6.7507 | 7.2163 | 6.9835 | 7.2163 | 6.9835 | 7.2163 | 7.2163 | 6.9835 | 7.2163 | 6.9835 | 7.2163 | 7.2163 | 6.5179 | 7.2163 | 6.9835 | 7.2163 | 6.9835 | 7.2163 | 7.2163 | 6.9835 | 7.2163 | 6.9835 | 6.5179
105 | Integrated Product Team / Working Group support | 2027-01-04 | 2029-12-31 | 430.5216 | 12.2106 | 11.0289 | 12.2106 | 11.8167 | 12.2106 | 11.8167 | 12.2106 | 12.2106 | 11.8167 | 12.2106 | 11.8167 | 12.2106 | 12.2106 | 11.4228 | 12.2106 | 11.8167 | 12.2106 | 11.8167 | 12.2106 | 12.2106 | 11.8167 | 12.2106 | 11.8167 | 12.2106 | 12.2106 | 11.0289 | 12.2106 | 11.8167 | 12.2106 | 11.8167 | 12.2106 | 12.2106 | 11.8167 | 12.2106 | 11.8167 | 11.0289
106a | Hazard Tracking System — establish | 2027-01-04 | 2027-04-04 | 120 | 40.8791 | 36.9231 | 40.8791 | 1.3187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106b | Hazard Tracking System — maintain | 2027-04-04 | 2029-12-31 | 263.3593 | 0 | 0 | 0 | 7.8771 | 8.1397 | 7.8771 | 8.1397 | 8.1397 | 7.8771 | 8.1397 | 7.8771 | 8.1397 | 8.1397 | 7.6146 | 8.1397 | 7.8771 | 8.1397 | 7.8771 | 8.1397 | 8.1397 | 7.8771 | 8.1397 | 7.8771 | 8.1397 | 8.1397 | 7.352 | 8.1397 | 7.8771 | 8.1397 | 7.8771 | 8.1397 | 8.1397 | 7.8771 | 8.1397 | 7.8771 | 7.352
107 | Hazard Management Progress Report | 2027-01-04 | 2029-12-31 | 143.5072 | 4.0702 | 3.6763 | 4.0702 | 3.9389 | 4.0702 | 3.9389 | 4.0702 | 4.0702 | 3.9389 | 4.0702 | 3.9389 | 4.0702 | 4.0702 | 3.8076 | 4.0702 | 3.9389 | 4.0702 | 3.9389 | 4.0702 | 4.0702 | 3.9389 | 4.0702 | 3.9389 | 4.0702 | 4.0702 | 3.6763 | 4.0702 | 3.9389 | 4.0702 | 3.9389 | 4.0702 | 4.0702 | 3.9389 | 4.0702 | 3.9389 | 3.6763
108 | Hazardous Materials Management Plan (HMMP) | 2027-01-04 | 2027-11-04 | 200 | 20.3279 | 18.3607 | 20.3279 | 19.6721 | 20.3279 | 19.6721 | 20.3279 | 20.3279 | 19.6721 | 20.3279 | 0.65574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | Preliminary Hazard List (PHL) | 2027-01-04 | 2027-04-04 | 160 | 54.5055 | 49.2308 | 54.5055 | 1.7582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | Preliminary Hazard Analysis (PHA) | 2027-04-04 | 2027-08-01 | 480 | 0 | 0 | 0 | 120 | 124 | 120 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | System Requirements Hazard Analysis (SRHA) | 2027-04-04 | 2028-05-04 | 520 | 0 | 0 | 0 | 39.2947 | 40.6045 | 39.2947 | 40.6045 | 40.6045 | 39.2947 | 40.6045 | 39.2947 | 40.6045 | 40.6045 | 37.9849 | 40.6045 | 39.2947 | 1.3098 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | Subsystem Hazard Analysis (SSHA) | 2027-11-04 | 2028-06-01 | 1872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 266.1611 | 275.0332 | 275.0332 | 257.2891 | 275.0332 | 266.1611 | 257.2891 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | System Hazard Analysis (SHA) | 2027-11-04 | 2028-06-29 | 832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104.4351 | 107.9163 | 107.9163 | 100.954 | 107.9163 | 104.4351 | 107.9163 | 90.5105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | Operating & Support Hazard Analysis (O&SHA) | 2028-05-04 | 2029-01-04 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.4878 | 58.5366 | 60.4878 | 60.4878 | 58.5366 | 60.4878 | 58.5366 | 60.4878 | 1.9512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | Health Hazard Analysis (HHA) | 2027-11-04 | 2028-05-04 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.9016 | 47.4317 | 47.4317 | 44.3716 | 47.4317 | 45.9016 | 1.5301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | Functional Hazard Analysis (FHA) | 2027-04-04 | 2027-11-04 | 520 | 0 | 0 | 0 | 72.5581 | 74.9767 | 72.5581 | 74.9767 | 74.9767 | 72.5581 | 74.9767 | 2.4186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | System-of-Systems Hazard Analysis | 2027-11-04 | 2028-05-04 | 0
210 | Environmental Hazard Analysis (EHA) | 2027-11-04 | 2028-05-04 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45.9016 | 47.4317 | 47.4317 | 44.3716 | 47.4317 | 45.9016 | 1.5301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | Safety Assessment Report (SAR) — ANCHOR | 2029-01-04 | 2029-10-04 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90.5109 | 81.7518 | 90.5109 | 87.5912 | 90.5109 | 87.5912 | 90.5109 | 90.5109 | 87.5912 | 2.9197 | 0 | 0
302 | Hazard Management Assessment Report (HMAR) | 2029-01-04 | 2029-10-04 | 0
303 | Test & Evaluation participation | 2028-12-10 | 2029-09-01 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60.1504 | 74.5865 | 67.3684 | 74.5865 | 72.1805 | 74.5865 | 72.1805 | 74.5865 | 69.7744 | 0 | 0 | 0 | 0
304 | Review of ECPs, change notices, deficiency reports, waivers | 2028-05-04 | 2029-12-31 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.514 | 23.7232 | 24.514 | 24.514 | 23.7232 | 24.514 | 23.7232 | 24.514 | 24.514 | 22.1417 | 24.514 | 23.7232 | 24.514 | 23.7232 | 24.514 | 24.514 | 23.7232 | 24.514 | 23.7232 | 22.1417
401 | Safety Verification (tests, demonstrations, induced/simulated failures) | 2028-05-04 | 2029-08-04 | 728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.2751 | 47.6856 | 49.2751 | 49.2751 | 47.6856 | 49.2751 | 47.6856 | 49.2751 | 49.2751 | 44.5066 | 49.2751 | 47.6856 | 49.2751 | 47.6856 | 49.2751 | 1.5895 | 0 | 0 | 0 | 0
402 | Explosives Hazard Classification Data | 2028-05-04 | 2029-01-04 | 0
403 | Explosive Ordnance Disposal Data | 2028-05-04 | 2029-01-04 | 0
SW-LOR | Software Level-of-Rigor tasks (Section 4.4, Table V) | 2027-11-04 | 2029-01-04 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.7383 | 45.1963 | 45.1963 | 42.2804 | 45.1963 | 43.7383 | 45.1963 | 43.7383 | 45.1963 | 45.1963 | 43.7383 | 45.1963 | 43.7383 | 45.1963 | 1.4579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOE-1 | System Safety Working Group meetings | 2027-01-04 | 2029-12-31 | 287.0144 | 8.1404 | 7.3526 | 8.1404 | 7.8778 | 8.1404 | 7.8778 | 8.1404 | 8.1404 | 7.8778 | 8.1404 | 7.8778 | 8.1404 | 8.1404 | 7.6152 | 8.1404 | 7.8778 | 8.1404 | 7.8778 | 8.1404 | 8.1404 | 7.8778 | 8.1404 | 7.8778 | 8.1404 | 8.1404 | 7.3526 | 8.1404 | 7.8778 | 8.1404 | 7.8778 | 8.1404 | 8.1404 | 7.8778 | 8.1404 | 7.8778 | 7.3526
LOE-2 | Design review safety data packages (SRR/PDR/CDR/TRR) | 2027-02-21 | 2029-01-04 | 320 | 0 | 5.1462 | 14.5029 | 14.0351 | 14.5029 | 14.0351 | 14.5029 | 14.5029 | 14.0351 | 14.5029 | 14.0351 | 14.5029 | 14.5029 | 13.5673 | 14.5029 | 14.0351 | 14.5029 | 14.0351 | 14.5029 | 14.5029 | 14.0351 | 14.5029 | 14.0351 | 14.5029 | 0.46784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LOE-3 | Safety program management, BOE/EVM upkeep, travel | 2027-01-04 | 2029-12-31 | 215.2608 | 6.1053 | 5.5145 | 6.1053 | 5.9083 | 6.1053 | 5.9083 | 6.1053 | 6.1053 | 5.9083 | 6.1053 | 5.9083 | 6.1053 | 6.1053 | 5.7114 | 6.1053 | 5.9083 | 6.1053 | 5.9083 | 6.1053 | 6.1053 | 5.9083 | 6.1053 | 5.9083 | 6.1053 | 6.1053 | 5.5145 | 6.1053 | 5.9083 | 6.1053 | 5.9083 | 6.1053 | 6.1053 | 5.9083 | 6.1053 | 5.9083 | 5.5145
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total hours / month |  |  | 11953.1992 | 275.6009 | 254.0761 | 296.6218 | 336.2504 | 340.6455 | 329.657 | 332.6455 | 216.6455 | 209.657 | 216.6455 | 626.6389 | 644.35 | 644.35 | 602.7791 | 644.35 | 623.5646 | 629.7849 | 342.3262 | 260.2096 | 260.2096 | 251.8157 | 260.2096 | 251.8157 | 320.3599 | 308.997 | 275.5922 | 305.12 | 295.2774 | 305.12 | 295.2774 | 305.12 | 252.6224 | 175.4114 | 93.6672 | 87.8201 | 81.9654
| FTE load (hours ÷ hours per FTE-month) |  |  |  | 1.7667 | 1.6287 | 1.9014 | 2.1555 | 2.1836 | 2.1132 | 2.1323 | 1.3888 | 1.344 | 1.3888 | 4.0169 | 4.1304 | 4.1304 | 3.864 | 4.1304 | 3.9972 | 4.0371 | 2.1944 | 1.668 | 1.668 | 1.6142 | 1.668 | 1.6142 | 2.0536 | 1.9807 | 1.7666 | 1.9559 | 1.8928 | 1.9559 | 1.8928 | 1.9559 | 1.6194 | 1.1244 | 0.60043 | 0.56295 | 0.52542
| Cumulative hours |  |  |  | 275.6009 | 529.677 | 826.2987 | 1162.5491 | 1503.1946 | 1832.8516 | 2165.4971 | 2382.1426 | 2591.7996 | 2808.4451 | 3435.084 | 4079.434 | 4723.7841 | 5326.5632 | 5970.9132 | 6594.4778 | 7224.2627 | 7566.5888 | 7826.7984 | 8087.0079 | 8338.8236 | 8599.0332 | 8850.8489 | 9171.2088 | 9480.2058 | 9755.798 | 10060.918 | 10356.1954 | 10661.3154 | 10956.5928 | 11261.7127 | 11514.3351 | 11689.7465 | 11783.4136 | 11871.2337 | 11953.1992

## Timeline
Program Timeline — milestones and 882E task windows (generated; do not type here)
Program: 2027-01-04 to 2029-12-31 ¦ Bars = task windows, ◆ = milestone
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Task | Name | Start | End | Hours | 2027-01-04 | 2027-02-04 | 2027-03-04 | 2027-04-04 | 2027-05-04 | 2027-06-04 | 2027-07-04 | 2027-08-04 | 2027-09-04 | 2027-10-04 | 2027-11-04 | 2027-12-04 | 2028-01-04 | 2028-02-04 | 2028-03-04 | 2028-04-04 | 2028-05-04 | 2028-06-04 | 2028-07-04 | 2028-08-04 | 2028-09-04 | 2028-10-04 | 2028-11-04 | 2028-12-04 | 2029-01-04 | 2029-02-04 | 2029-03-04 | 2029-04-04 | 2029-05-04 | 2029-06-04 | 2029-07-04 | 2029-08-04 | 2029-09-04 | 2029-10-04 | 2029-11-04 | 2029-12-04
MILESTONES
| Program Start | 2027-01-04 | bar: 1
| SRR | 2027-04-04 | bar: 4
| SFR | 2027-07-04 | bar: 7
| PDR | 2027-11-04 | bar: 11
| CDR | 2028-05-04 | bar: 17
| TRR | 2029-01-04 | bar: 25
| Test Start | 2029-02-04 | bar: 26
| Test Complete | 2029-08-04 | bar: 32
| SAR Submittal | 2029-10-04 | bar: 34
| Program End | 2029-12-31 | bar: 36
TASKS
101 | Hazard identification & mitigation effort using the system safety methodology (program execution) | 2027-01-04 | 2029-12-31 | 717.5359 | bar: 1 to 36
102 | System Safety Program Plan (SSPP) | 2027-01-04 | 2027-04-04 | 320 | bar: 1 to 4
103 | Hazard Management Plan (HMP) — other functional disciplines
104 | Support of Government reviews / audits / boards | 2027-03-07 | 2029-12-31 | 240 | bar: 3 to 36
105 | Integrated Product Team / Working Group support | 2027-01-04 | 2029-12-31 | 430.5216 | bar: 1 to 36
106a | Hazard Tracking System — establish | 2027-01-04 | 2027-04-04 | 120 | bar: 1 to 4
106b | Hazard Tracking System — maintain | 2027-04-04 | 2029-12-31 | 263.3593 | bar: 4 to 36
107 | Hazard Management Progress Report | 2027-01-04 | 2029-12-31 | 143.5072 | bar: 1 to 36
108 | Hazardous Materials Management Plan (HMMP) | 2027-01-04 | 2027-11-04 | 200 | bar: 1 to 11
201 | Preliminary Hazard List (PHL) | 2027-01-04 | 2027-04-04 | 160 | bar: 1 to 4
202 | Preliminary Hazard Analysis (PHA) | 2027-04-04 | 2027-08-01 | 480 | bar: 4 to 7
203 | System Requirements Hazard Analysis (SRHA) | 2027-04-04 | 2028-05-04 | 520 | bar: 4 to 17
204 | Subsystem Hazard Analysis (SSHA) | 2027-11-04 | 2028-06-01 | 1872 | bar: 11 to 17
205 | System Hazard Analysis (SHA) | 2027-11-04 | 2028-06-29 | 832 | bar: 11 to 18
206 | Operating & Support Hazard Analysis (O&SHA) | 2028-05-04 | 2029-01-04 | 480 | bar: 17 to 25
207 | Health Hazard Analysis (HHA) | 2027-11-04 | 2028-05-04 | 280 | bar: 11 to 17
208 | Functional Hazard Analysis (FHA) | 2027-04-04 | 2027-11-04 | 520 | bar: 4 to 11
209 | System-of-Systems Hazard Analysis
210 | Environmental Hazard Analysis (EHA) | 2027-11-04 | 2028-05-04 | 280 | bar: 11 to 17
301 | Safety Assessment Report (SAR) — ANCHOR | 2029-01-04 | 2029-10-04 | 800 | bar: 25 to 34
302 | Hazard Management Assessment Report (HMAR)
303 | Test & Evaluation participation | 2028-12-10 | 2029-09-01 | 640 | bar: 24 to 32
304 | Review of ECPs, change notices, deficiency reports, waivers | 2028-05-04 | 2029-12-31 | 480 | bar: 17 to 36
401 | Safety Verification (tests, demonstrations, induced/simulated failures) | 2028-05-04 | 2029-08-04 | 728 | bar: 17 to 32
402 | Explosives Hazard Classification Data
403 | Explosive Ordnance Disposal Data
SW-LOR | Software Level-of-Rigor tasks (Section 4.4, Table V) | 2027-11-04 | 2029-01-04 | 624 | bar: 11 to 25
LOE-1 | System Safety Working Group meetings | 2027-01-04 | 2029-12-31 | 287.0144 | bar: 1 to 36
LOE-2 | Design review safety data packages (SRR/PDR/CDR/TRR) | 2027-02-21 | 2029-01-04 | 320 | bar: 2 to 25
LOE-3 | Safety program management, BOE/EVM upkeep, travel | 2027-01-04 | 2029-12-31 | 215.2608 | bar: 1 to 36
| FTE load (from Phasing) |  |  |  | 1.7667 | 1.6287 | 1.9014 | 2.1555 | 2.1836 | 2.1132 | 2.1323 | 1.3888 | 1.344 | 1.3888 | 4.0169 | 4.1304 | 4.1304 | 3.864 | 4.1304 | 3.9972 | 4.0371 | 2.1944 | 1.668 | 1.668 | 1.6142 | 1.668 | 1.6142 | 2.0536 | 1.9807 | 1.7666 | 1.9559 | 1.8928 | 1.9559 | 1.8928 | 1.9559 | 1.6194 | 1.1244 | 0.60043 | 0.56295 | 0.52542